## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team and Freshman Seminar acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions, cross-team testing, and Freshman Seminar testing.
Team Name | 2211-swen-261-02-A Opple
Testing Team Name | fill in when doing cross-team or Freshman Seminar testing

## Test Plan
User Story | Acceptance Criterion | Sprint 1 | Tester initials; date; comments (required if test failed) | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a Player I want to sign-in so that I can play a game of checkers. | Given that I have not yet signed in when I see the Home page then I must see a means to sign-in. (such as a link or button) |  | WH,10/6/21,success; MH,10/6/21,success |  | All of this was tested and passed, but the document was not updated |  | Pass;QT;11/8/21 Pass;RO;11/8/21 Pass;MH;11/14/21; Pass;SC;11/15/21; Pass;MP;11/15/21;
| Given that I am not signed-in when I do click on the sign-in link then I expect to be taken to the Sign-in page, with a means to enter a player name. |  | WH,10/6/21,success; MH,10/6/21,success |  | All of this was tested and passed, but the document was not updated |  | Pass;QT;11/8/21 Pass;RO;11/8/21 Pass;MH;11/14/21; Pass;SC;11/15/21; Pass;MP;11/15/21;
| Given that no one else is using my name when I enter my name containing at least one alphanumeric character and optionally spaces in the sign-in form and click the Sign-in button then I expect the system to reserve my name and navigate back to the Home page. |  | WH,10/6/21,success; MH,10/6/21,success |  | All of this was tested and passed, but the document was not updated |  | Pass;QT;11/8/21 Pass;RO;11/8/21 Pass;MH;11/14/21; Pass;SC;11/15/21; Pass;MP;11/15/21;
| Given that I am on the Sign-in page when I enter a name that does not contain at least one alphanumeric character or contains one or more characters that are not alphanumeric or spaces and click the Sign-in button then I expect the system to reject this name and return the Sign-in page. |  | WH,10/6/21,success; MH,10/6/21,success |  | All of this was tested and passed, but the document was not updated |  | Pass;QT;11/8/21 Pass;RO;11/8/21 Pass;MH;11/14/21; Pass;SC;11/15/21; Pass;MP;11/15/21;
| Given that someone else with my name has signed-in when I enter my name in the Sign-in form and click the Sign-in button then I expect the system to reject my sign-in and return the Sign-in page for me to try a different name. |  | WH,10/6/21,success; MH,10/6/21,success |  | All of this was tested and passed, but the document was not updated |  | Pass;QT;11/8/21 Pass;RO;11/8/21 Pass;MH;11/14/21; Pass;SC;11/15/21; Pass;MP;11/15/21;
| Given that I am signed-in when I navigate to the Home page then I expect to see a list of all other signed-in players. (NOTE: in the next story you will use this list to pick opponents for checkers games.) |  | WH,10/6/21,success; MH,10/6/21,success |  | All of this was tested and passed, but the document was not updated |  | Pass;QT;11/8/21 Pass;RO;11/8/21 Pass;MH;11/14/21; Pass;SC;11/15/21; Pass;MP;11/15/21;
| Given that I am not signed-in when I navigate to the Home page then I expect to see a message of how many players are signed-in but not a list of them (for privacy reasons). |  | WH,10/6/21,success; MH,10/6/21,success |  | All of this was tested and passed, but the document was not updated |  | Pass;QT;11/8/21 Pass;RO;11/8/21 Pass;MH;11/14/21; Pass;SC;11/15/21; Pass;MP;11/15/21;
As a Player I want to start a game so that I can play checkers with an opponent. | Given that I'm signed in when I view the Home page then I can start a game by selecting a player listed on the Home page. |  | JM,10/5/2021,success MP, 10/5/2021, success |  | All of this was tested and passed, but the document was not updated |  | Pass;QT;11/8/21 Pass;RO;11/8/21 Pass;MH;11/14/21; Pass;SC;11/15/21; Pass;MP;11/15/21;
| Given that the player I selected isn't yet in a game when I select that player then the system will begin a checkers game and assign me as the starting (Red) player and my opponent as the White player. |  | JM,10/5/2021,success MP, 10/5/2021, success |  | All of this was tested and passed, but the document was not updated |  | Pass;QT;11/8/21 Pass;RO;11/8/21 Pass;MH;11/14/21; Pass;SC;11/15/21; Pass;MP;11/15/21;
| Given that the player I selected is already in a game when I select that player then the system will return me to the Home page with an error message. |  | JM,10/5/2021,success MP, 10/5/2021, success |  | All of this was tested and passed, but the document was not updated |  | Pass;QT;11/8/21 Pass;RO;11/8/21 Pass;MH;11/14/21; Pass;SC;11/15/21; Pass;MP;11/15/21;
| Given that I'm waiting for a game when another player selects a game with me then the system will automatically send me to the Game View as the White player. NOTE: the `home.ftl` HTML includes a `<meta>` tag that tells the browser to refresh the game every 5 seconds; thus you need to update the `GetHomeRoute` controller to handle the situation when a player is assigned a game. |  | JM,10/5/2021,success MP, 10/5/2021, success |  | All of this was tested and passed, but the document was not updated |  | Pass;QT;11/8/21 Pass;RO;11/8/21 Pass;MH;11/14/21; Pass;SC;11/15/21; Pass;MP;11/15/21;
| Given a valid, initial game board when I drag a piece to a white space then the piece should not be droppable. |  | JM,10/5/2021,success MP, 10/5/2021, success |  | All of this was tested and passed, but the document was not updated |  | Pass;QT;11/8/21 Pass;RO;11/8/21 Pass;MH;11/14/21; Pass;SC;11/15/21; Pass;MP;11/15/21;
| Given a valid, initial game board when I drag a piece to an occupied space then the piece should not be droppable. |  | JM,10/5/2021,success MP, 10/5/2021, success |  | All of this was tested and passed, but the document was not updated |  | Pass;QT;11/8/21 Pass;RO;11/8/21 Pass;MH;11/14/21; Pass;SC;11/15/21; Pass;MP;11/15/21;
| Given a valid, initial game board when I drag a piece to an open space then the piece should be droppable. NOTE: In this Story the drop action should not do anything; piece movement will be the focus of future stories. |  | JM,10/5/2021, have a second check MP, 10/5/2021, successful but when the piece is already dragged to a new spot, there is some highlight issues if that piece is moved again (See https://imgur.com/a/H7nObve). The piece also reset to original spot on refresh. I believe both "issues" are part of Sprint 2. |  | All of this was tested and passed, but the document was not updated |  | Pass;QT;11/8/21 Pass;RO;11/8/21 Pass;MH;11/14/21; Pass;SC;11/15/21; Pass;MP;11/15/21;
| Given a valid, initial game board when I view the board in the browser then my pieces are oriented on the bottom of the board grid just like I would see the board if I were playing in the physical world. |  | JM,10/5/2021, success MP, 10/5/2021, success |  | All of this was tested and passed, but the document was not updated |  | Pass;QT;11/8/21 Pass;RO;11/8/21 Pass;MH;11/14/21; Pass;SC;11/15/21; Pass;MP;11/15/21;
As a Player, I want the Red Player to move first so it will start the game. | Given that game has just begun when I am the red player then I expect to move first. |  |  |  | All of this was tested and passed, but the document was not updated |  | Pass;TB;11/8/21 Pass;CM:11/8/21 Pass;MH;11/14/21; Pass;SC;11/15/21; Pass;MP;11/15/21;
| Given that game has just begun when I am the white player then I expect to not be able to move first. |  |  |  | All of this was tested and passed, but the document was not updated |  | Pass;TB;11/8/21 Pass;CM:11/8/21 Pass;MH;11/14/21; Pass;SC;11/15/21; Pass;MP;11/15/21;
As a Player, I want to see the time of the game I am in so that I do not lose the track of time. | Given that the game has started when time has progressed then I expect to see the time elapsed since game start | [5 empty] | Fail;TB;11/8/21; do not see any time indicator Fail;MH;11/14/21;Not implemented and not part of MVPPass
As a Player, I want to see how many pieces my opponent and I have lost so that I can plan my moves more carefully and accordingly. | Given that the game has started when I am playing the game then I expect to see how many pieces my opponent and I have lost. | [5 empty] | Fail;TB;11/8/21; do not see any pieces lost count Fail;MH;11/14/21;Not implemented and not part of MVP
| Given the game is in progress when I take a player piece then I expect to see the amount of taken pieces update | [5 empty] | Fail;TB;11/8/21; do not see any pieces lost count Fail;MH;11/14/21;Not implemented and not part of MVP
| Given the game is in progress when the opponent takes a piece then I expect to see the amount of taken pieces update | [5 empty] | Fail;TB;11/8/21; do not see any taken pieces count Fail;MH;11/14/21;Not implemented and not part of MVP
As a Player, I want to win the game by capturing all the opponents pieces or they are unable to move so that I become victorious. | Given that the opponent has one piece left when I take the last piece then I expect to win and the game to end. |  |  |  | All of this was tested and passed, but the document was not updated |  | Pass;TB;11/8/21 Pass;CM:11/8/21 Pass;MH;11/14/21; Pass;SC;11/15/21; Pass;MP;11/15/21;
| Given that the opponent is out of moves then when I attempt to make a move then I expect to win and the game to end. |  |  |  | All of this was tested and passed, but the document was not updated |  | Pass;TB;11/8/21 Pass;CM:11/8/21 ; no moves are counted Pass;MH;11/14/21; Pass;SC;11/15/21; Pass;MP;11/15/21;
As a Player, I want to lose the game when all my pieces are captured or when no moves can be made so that I can leave and/or join a new game. | Given that I am out of moves when an opponent attempts to make a move then I expect to lose and game to end. |  |  |  | All of this was tested and passed, but the document was not updated |  | Pass;TB;11/8/21 Pass;CM:11/8/21 Pass;MH;11/14/21; Pass;SC;11/15/21; Pass;MP;11/15/21;
| Given that I have one piece left when the opponent takes the last piece then I expect to lose and game to end |  |  |  | All of this was tested and passed, but the document was not updated |  | Pass;TB;11/8/21 Pass;CM:11/8/21 Pass;MH;11/14/21; Pass;SC;11/15/21; Pass;MP;11/15/21;
As a Player, I want to move one square diagonally. | Given that it is my turn when I attempt to move diagonally then I expect the move to be valid and the piece to drop on the square. |  |  |  | All of this was tested and passed, but the document was not updated |  | Pass;TB;11/8/21 Pass;CM:11/8/21 Pass;MH;11/14/21; Pass;SC;11/15/21; Pass;MP;11/15/21;
| Given that it is my turn when I attempt to place my piece on an occupied space diagonally then I expect the piece to return to the original square. |  |  |  | All of this was tested and passed, but the document was not updated |  | Pass;TB;11/8/21 Pass;CM:11/8/21 Pass;MH;11/14/21; Pass;SC;11/15/21; Pass;MP;11/15/21;
| Given I attempt to move horizontally, backward as a non-king, or vertically when I drop the piece then it returns to the original square. |  |  |  | All of this was tested and passed, but the document was not updated |  | Pass;TB;11/8/21 Pass;CM:11/8/21 Pass;MH;11/14/21; Pass;SC;11/15/21; Pass;MP;11/15/21;
| Given that I attempt to move a piece to a spot not adjacent to it when I drop the piece then I expect the piece to return to the original square. |  |  |  | All of this was tested and passed, but the document was not updated |  | Pass;TB;11/8/21 Pass;CM:11/8/21 Pass;MH;11/14/21; Pass;SC;11/15/21; Pass;MP;11/15/21;
| Given that it is not my turn when I move a piece then I expect the piece to return to its original square. |  |  |  | All of this was tested and passed, but the document was not updated |  | Pass;TB:11/8/21; cannot move when not your turn but there is no message Pass;MH;11/14/21; Pass;MP;11/15/21; Pass;SC;11/15/21;
| Given that I made a move when I submit my turn then I expect it to be registered and displayed on the board for both players. |  |  |  | All of this was tested and passed, but the document was not updated |  | Pass;TB:11/8/21 Pass;MH;11/14/21; Pass;MP;11/15/21; Pass;SC;11/15/21;
| Given that the simple move has happened when the last square that the piece lands on is furthest from me then I expect that piece to become a king. |  |  |  | All of this was tested and passed, but the document was not updated |  | Pass;TB;11/8/21 Pass;MH;11/14/21; Pass;MP;11/15/21; Pass;SC;11/15/21;
As a Player, I want to move two squares diagonally, over another players piece (and take it) so that I can get closer to winning the game. | Given that there is an opponents piece in the way to a directly adjacent diagonal square when I make a move over it then I expect to capture that piece. |  |  |  | All of this was tested and passed, but the document was not updated |  | Pass;TB;11/8/21 Pass;MH;11/14/21; Pass;MP;11/15/21; Pass;SC;11/15/21;
| Given that there is an opponent's piece directly behind a piece in the way when I make a move over it then I expect to not be able to jump over that piece. |  |  |  | All of this was tested and passed, but the document was not updated |  | Pass;TB;11/8/21 Pass;MH;11/14/21; Pass;MP;11/15/21; Pass;SC;11/15/21;
| Given that there is an opponents piece not directly diagonal to my piece when I attempt to jump that piece then my piece should return to the original square and an error message printed. |  |  |  | All of this was tested and passed, but the document was not updated |  | Pass;TB;11/8/21; piece is not able to move but there is no error message Pass;MH;11/14/21; Pass;MP;11/15/21; Pass;SC;11/15/21;
| Given that there is at least one simple jump move option available when it is my turn then I expect to choose only one move. |  |  |  | All of this was tested and passed, but the document was not updated |  | Pass;TB;11/8/21 Pass;MH;11/14/21; Pass;MP;11/15/21; Pass;SC;11/15/21;
| Given that the simple jump move has happened when the last square that the piece lands on is furthest from me then I expect that piece to become a king. |  |  |  | All of this was tested and passed, but the document was not updated |  | Pass;TB;11/8/21 Pass;MH;11/14/21; Pass;MP;11/15/21; Pass;SC;11/15/21;
As a Player, I want to chain multiple valid single jump moves so that I can get closer to winning the game. | Given that an opponent has multiple pieces diagonally from my piece without any empty spaces between when I attempt to jump over more than one piece then I expect to have my piece return to original spot and error printed. |  |  |  | All of this was tested and passed, but the document was not updated |  | Pass;TB;11/8/21 Pass;MH;11/14/21; Pass;MP;11/15/21; Pass;SC;11/15/21;
| Given that there are more than one opponent's pieces in the way with connecting empty squares behind them when I make my move then I expect to jump over those pieces and capture them. |  |  |  | All of this was tested and passed, but the document was not updated |  | Pass;TB;11/8/21 Pass;MH;11/14/21; Pass;MP;11/15/21; Pass;SC;11/15/21;
| Given that I do not want to do this anymore when I leave my computer then I expect to be happier. |  |  |  | All of this was tested and passed, but the document was not updated |  | Pass;TB;11/8/21; Pass;MH;11/14/21; Pass;MP;11/15/21; Pass;SC;11/15/21;
| Given that there is at least one multiple jump move option available when it is my turn then I expect to choose only one move. |  |  |  | All of this was tested and passed, but the document was not updated |  | Pass;TB;11/8/21 Pass;MH;11/14/21; Pass;MP;11/15/21; Pass;SC;11/15/21;
| Given that the multiple jump move has happened when the last square that the piece lands on is furthest from me then I expect that piece to become a king. |  |  |  | All of this was tested and passed, but the document was not updated |  | Pass;TB;11/8/21 Pass;MH;11/14/21; Pass;MP;11/15/21; Pass;SC;11/15/21;
As a Player, I want to be able to not stop once starting a multiple jump move so that I adhere to the American Rules for Checkers | Given that a multiple jump move option is available when I commence that move then I expect to not be able to stop the chain move until the last opponent with an empty square behind it is captured. |  |  |  | All of this was tested and passed, but the document was not updated |  | Pass;TB;11/8/21 Pass;MH;11/14/21; Pass;MP;11/15/21; Pass;SC;11/15/21;
| Given that a multiple jump move option is commencing when I am watching the move happening then I expect to see the demise of that true soldier piece dying to capture the weakling pieces. |  |  |  | All of this was tested and passed, but the document was not updated |  | Pass;TB;11/8/21 Pass;MH;11/14/21; Pass;MP;11/15/21; Pass;SC;11/15/21;
As a Player, I want to be unable to put down a piece once I pick it up, so I have to move that piece. | Given there is no opponent piece on the other side of the piece I am jumping when I jump said piece then I expect to stop on the other side on the removed piece. |  |  |  | All of this was tested and passed, but the document was not updated |  | Pass;TB;11/8/21 Pass;MH;11/14/21; Pass;MP;11/15/21; Pass;SC;11/15/21;
| Given that there is a piece on the other side of an opponent's piece when I attempt to take the piece then I should have my piece returned to its original position. |  |  |  | All of this was tested and passed, but the document was not updated |  | Pass;TB;11/8/21; no invalid move displayed Pass;MH;11/14/21; Pass;MP;11/15/21; Pass;SC;11/15/21;
As a Player, I want my piece to become a king piece when it reaches the opponents side so that I can move that king piece diagonally forward and backward. | Given that a move has happened when the square that a piece lands on is furthest from me then I expect the piece to become a king. |  |  |  | All of this was tested and passed, but the document was not updated |  | Pass;TB;11/8/21 Pass;CM:11/8/21 Pass;MH;11/14/21; Pass;MP;11/15/21; Pass;SC;11/15/21;
| Given I am using a king piece when I attempt to make a diagonal move in any direction that is not occupied then the piece should be placed there. |  |  |  | All of this was tested and passed, but the document was not updated |  | Pass;TB;11/8/21 Pass;CM:11/8/21 Pass;MH;11/14/21; Pass;MP;11/15/21; Pass;SC;11/15/21;
| Given that I am using a king piece when I attempt to make a diagonal jump move in any direction that has an opponent's piece and empty square behind it then the king piece should capture the piece and land on the empty square behind the captured piece. |  |  |  | All of this was tested and passed, but the document was not updated |  | Pass;TB;11/8/21 Pass;CM:11/8/21 Pass;MH;11/14/21; Pass;MP;11/15/21; Pass;SC;11/15/21;
| Given that I am using a king piece when I attempt to make a diagonal multiple jump move in any direction that has multiple opponents pieces with each one having an empty space behind it then I expect the king piece to capture those pieces and stop at the last empty square in that chain. |  |  |  | All of this was tested and passed, but the document was not updated |  | Pass;TB;11/8/21 Pass;CM:11/8/21 Pass;MH;11/14/21; Pass;MP;11/15/21; Pass;SC;11/15/21;
| Given that a piece is a king when it lands on the square that is farthest from me then I do not expect the piece to turn to normal. |  |  |  | All of this was tested and passed, but the document was not updated |  | Pass;TB;11/8/21 Pass;CM:11/8/21 Pass;MH;11/14/21; Pass;MP;11/15/21; Pass;SC;11/15/21;
As a Player, I want to forfeit with a press of a button so that I do not have to be more ashamed of myself and/or so that I can join a new game. | Given that I want to leave a game when I press the RESIGN button then I expect to return to the home page. |  |  |  | All of this was tested and passed, but the document was not updated |  | Pass;QT;11/8/21 Pass;RO;11/8/21 Pass;MH;11/14/21; Pass;MP;11/15/21; Pass;SC;11/15/21;
| Given that I want to leave a game when I press resign then the opponent should win the game. |  |  |  | All of this was tested and passed, but the document was not updated |  | Pass;TB;11/8/21 Pass;MH;11/14/21; Pass;MP;11/15/21; Pass;SC;11/15/21;
| Given that I want to leave a game when I press resign then I should lose and bring dishonor and shame to my family. |  |  |  | All of this was tested and passed, but the document was not updated |  | Pass;TB;11/8/21; are you Mulan? Pass;MH;11/14/21; Pass;MP;11/15/21;Pass;SC;11/15/21;
| Given that I resign when I leave from my computer then I expect to be forced to commit seppuku by Japanese 7-foot-tall samurai in real life. |  |  |  | All of this was tested and passed, but the document was not updated |  | Fail;TB;11/8/21;are you okay? Fail;MH;11/14/21;No, no we are not. Pass;MP;11/15/21; Pass;SC;11/15/21;
As a Player, I want the game to display a forfeit confirmation so that I do notaccidentally forfeit in a winning situation. | Given that I want to leave the game when I press the resign button then I expect the system to confirm I am resigning. |  |  |  | All of this was tested and passed, but the document was not updated |  | Pass;TB;11/8/21 Pass;MH;11/14/21; Pass;MP;11/15/21; Pass;SC;11/15/21;
As a Spectator, I want to spectate any ongoing/new games so that I can learn new moves. | Given that I am not in a game or spectating when I load the home page then I expect to be able to see which players are currently in a game. | [5 empty] | Pass;MH;11/14/21 Pass;MP;11/15/21; Pass;SC;11/15/21;
| Given that I am on the home page when I click a spectate button then I expect to be taken to the in progress game as a spectator. | [5 empty] | Pass;MH;11/14/21 Pass;MP;11/15/21; Pass;SC;11/15/21;
| Given that I am spectating a game when a player makes a move then I expect my view of the board to update with the move that was made. | [5 empty] | Pass;MH;11/14/21 Pass;MP;11/15/21; Pass;SC;11/15/21;
| Given that I am spectating a game when I am waiting for a move to be made then I expect to see a timer of how long ago the last move was. | [5 empty] | Pass;MH;11/14/21 Pass;MP;11/15/21; Pass;SC;11/15/21;
As a Spectator, I do not want to be able to move the pieces of both players so that I do not mess up each players moves. | Given that I am spectating a game when I try to interact with the board then I expect nothing to happen. | [5 empty] | Pass;MH;11/14/21 Pass;MP;11/15/21; Pass;SC;11/15/21;
As a Spectator, I want to be able to leave at any time and return to the browser so that I can play myself or spectate another game. | Given that I am spectating a game when I click the exit button then I expect to be returned to the home page. | [5 empty] | Pass;MH;11/14/21 Pass;MP;11/15/21; Pass;SC;11/15/21;
As a Player, I want to play against the server AI so that I may play something besides another human. | Given that I am lonely when I load the home page then I expect to see a button to challenge an AI to practice. | [5 empty] | Pass;QT;11/8/21 Pass;MH;11/14/21; Pass;MP;11/15/21; Pass;SC;11/15/21;
| Given that I am not in a game or spectating when I load the home page then I expect to see a button to challenge an AI to practice. | [5 empty] | Pass;QT;11/8/21 Pass;MH;11/14/21; Pass;MP;11/15/21; Pass;SC;11/15/21;
| Given that I want to play against an AI and am not in a game when I press the challenge AI button then I expect to be taken into a new game against an AI as the Red player. | [5 empty] | Pass;TB;11/8/21 Pass;MH;11/14/21; Pass;SC;11/15/21; Pass;MP;11/15/21;
As a Player, I want the AI to make a valid move when it is its turn and when the game has not ended so that the game can be played and won by a God of Checkers like me. | Given that I am in a game against an AI when I move a piece then I expect to be subjected to the same rules as a normal game of checkers against another player. | [5 empty] | Pass;QT;11/8/21 Pass;MH;11/14/21; Pass;MP;11/15/21; Pass;SC;11/15/21;
| Given that I am in a game against an AI when the AI moves a piece then I expect the AI to also follow the same rules as I have to. | [5 empty] | Pass;QT;11/8/21 Pass;MH;11/14/21; Pass;MP;11/15/21; Pass;SC;11/15/21;
As a Player, I want the AI to automatically end the game if either I win or lose the match so that the game may end normally. | Given that the AI has one piece left when I take the last piece then I expect to win and the game to end. | [5 empty] | Pass;TB;11/8/21 Pass;CM:11/8/21 Pass;MH;11/14/21; Pass;MP;11/15/21; Pass;SC;11/15/21;
| Given that the AI is unable to move then when the AI attempts to make a move then I expect to win and the game to end. | [5 empty] | Pass;TB;11/8/21 Pass;CM:11/8/21 Pass;MH;11/14/21; Pass;SC;11/15/21; Pass;MP;11/15/21;
| Given that I have one piece left when the AI takes the last piece then I expect to lose and game to end. | [5 empty] | Pass;TB;11/8/21 Pass;CM:11/8/21 Pass;MH;11/14/21; Pass;SC;11/15/21; Pass;MP;11/15/21;
| Given that I am out of moves when the AI attempts to make a move then I expect to lose and the game to end. | [5 empty] | Pass;TB;11/8/21 Pass;CM:11/8/21 ; no moves are counted Pass;MH;11/14/21; Pass;SC;11/15/21; Pass;MP;11/15/21;
As a Player, I want the AI Player to automatically quit whenever I choose to leave the game so that there is not an infinitely stopped checkers game occurring on the server. | Given that I want to leave a game when I press the RESIGN button then I expect to return to the home page. | [5 empty] | Pass;TB;11/8/21 Pass;CM:1 Pass;MH;11/14/21;1/8/21 Pass;MP;11/15/21; Pass;SC;11/15/21;
| Given that I want to leave a game when I press the RESIGN button then I expect the game to terminate and get cleaned up. | [5 empty] | Pass;TB;11/8/21 Pass;CM:11/8/21 Pass;MH;11/14/21; Pass;MP;11/15/21; Pass;SC;11/15/21;